## Start here
VerifiCasa — work plan
Made 23 Oct 2026. Open 'Tasks', do the rows where Who = You, change Status from the dropdown. Claude does the rest next session.
Progress | Count
Total tasks | 17
Done | 0
Blocked | 0
Open for You | 7
Open for Claude | 8
Open P0 (do now) | 4
% done | 0%
Tomorrow, in order
1. You: install Claude GitHub App on iamvava7 (T01)
2. You: add INTEGRATIONS_MASTER_KEY in Base44 (T04)
3. Claude: push SpaceTwin commits (T02)
4. Both: test admin panel in preview (T05)
5. You: answer 'Questions for you' tab
Legend
Yellow cells | for you to fill in
Blue numbers | inputs you can change (Suggestions)
Dropdowns | Who / Priority / Status / Decision
Green / red / yellow rows | Done / Blocked / In progress
Never write | API keys or passwords in this file

## Tasks
ID | Area | Task | Who | Priority | Status | Depends on | How / notes | Done date
T01 | GitHub | Install the Claude GitHub App on the iamvava7 account and give it the 'yes' repo | You | P0 – now | To do |  | Sign in as iamvava7 → github.com/apps/claude/installations/select_target → iamvava7 → repo 'yes'. If still blocked, start a new session with iamvava7/yes selected.
T02 | GitHub | Push the 3 waiting SpaceTwin commits (tour page, tour quality, Maria) | Claude | P0 – now | To do | T01 | Branch 'spacetwin'. Backup: spacetwin-unpushed.bundle (git pull <bundle> spacetwin).
T03 | GitHub | Make repos private (if still wanted) | You | P2 – later | To do | T02 | GitHub → repo → Settings → Danger zone → Change visibility. Testers then need an invite to clone.
T04 | Website | Add the secret INTEGRATIONS_MASTER_KEY in Base44 | You | P0 – now | To do |  | Base44 → Settings → Secrets. Long random phrase (min 16 chars). Never share it or put it in the repo.
T05 | Website | Test branch claude/admin-integrations-texts in Base44 preview | Both | P0 – now | To do | T04 | Admin → 'Integrări & chei API': save + Test a Stripe key. Admin → 'Texte site': change one text, check it appears live, then 'Original'.
T06 | Website | Merge claude/admin-integrations-texts into main | Claude | P1 – next | To do | T05 | Only after your OK. Base44 publishes from main.
T07 | Maria AI | Add the Anthropic API key so Maria uses Claude | You | P1 – next | To do | T02 | console.anthropic.com → API key → set ANTHROPIC_API_KEY on the tour server (or in the new admin panel). Without it Maria still answers from listing facts.
T08 | Hosting | Choose where the tour app (SpaceTwin) runs | You | P1 – next | To do |  | Needs Node + Python + OpenCV for the pro stitcher. Options: small VPS (Hetzner/DigitalOcean), Render, Fly.io.
T09 | Hosting | Deploy SpaceTwin + connect it to verificasa.ro (/3D links) | Claude | P1 – next | To do | T02, T08 | Set VERIFICASA env (app id), domain, HTTPS. Check embed iframe on a listing.
T10 | Capture | Decide: phone only, or also a 360° camera (e.g. Insta360) | You | P1 – next | To do |  | Changes the capture flow; a 360° camera gives Teleport/Matterport-level quality fastest.
T11 | Capture | Real-home test: capture 1 apartment with a phone, review quality | Both | P1 – next | To do | T09 | Send me the result link; I tune stitching/exposure on real footage.
T12 | Website | Fix Tur 3D page copy + add 'Tur 3D' search filter | Claude | P2 – later | To do | T06
T13 | Website | Floor-plan tab on each listing | Claude | P2 – later | To do | T09
T14 | Website | Energy class (CPE) + price/m² on listing cards | Claude | P2 – later | To do | T06 | Law 372/2005 already requires the energy certificate.
T15 | Website | 'Noua Casă' mortgage calculator | Claude | P2 – later | To do | T06 | 2026 rules: 5% deposit ≤ €70k, 15% ≤ €140k — re-check before launch.
T16 | Website | 'Verified on site' badge from GPS capture stamp | Claude | P1 – next | To do | T09 | Backend already stores the capture stamp.
T17 | Figma | Review the Figma tour viewer vs the built page and send changes | You | P2 – later | To do | T09 | Figma page '🌐 Web · 3D Tour viewer'.

## Done so far
Repo | Branch | Commit | What changed | On GitHub?
iamvava7/yes | spacetwin | a4ab7c1 | Pro OpenCV stitcher (hides seams, no ghosting), VerifiCasa look, listing embed + /3D links | Yes
iamvava7/yes | spacetwin | 5a0b53a | Tour page rebuilt from Figma 'Web · 3D Tour viewer' (PC + phone, details panel, room strip, loading) | No – waiting T02
iamvava7/yes | spacetwin | 6701ee7 | Tour quality: sharper 360°, 2D plan with room sizes + wall lengths, dollhouse studio look, measure snapping, tiny-planet intro, labels; VerifiCasa listings in the app, verified-on-site stamp | No – waiting T02
iamvava7/yes | spacetwin | 984f06e | Maria AI agent: only about this home, RO/EN, map card, go-to-room, call/WhatsApp/email, voice | No – waiting T02
vava6969/verificasa | claude/admin-integrations-texts | (latest) | Admin 'Integrări & chei API' (encrypted keys, test, delete, custom) + 'Texte site' live editor (RO/EN) | Yes – not merged
vava6969/verificasa | main | (existing) | Live Stripe price editing already exists: Admin → 'Planuri & Prețuri' | —

## Suggestions
# | Idea | Why it helps (Romania) | Inspired by | Impact (1-5) | Effort (1-5) | Score | Decision
1 | Verified-on-site badge (GPS + date of capture) | Fake listings are a big trust problem in Romanian portals | Original (VerifiCasa) | 5 | 2 | 8
2 | 'Tur 3D' filter + floor-plan tab | Listings with tours/plans get more views and saves | Zillow, Immoweb | 5 | 2 | 8
3 | Energy class (CPE) + price/m² on cards | Buyers compare by price/m²; CPE is legally required | ImmoScout24 | 4 | 1 | 7
4 | Seismic risk class field (Bucharest!) | Seismic class is going into the land register; huge concern in Bucharest | Original | 5 | 2 | 8
5 | Noua Casă / mortgage calculator | Most buyers finance; shows real monthly cost | Zillow BuyAbility | 4 | 2 | 6
6 | Neighbourhood layers: schools, metro, noise, parks | Location is the #1 question; Maria can use it too | Zoopla | 4 | 3 | 5
7 | Agent dashboard: tour views, Maria chats, leads | Proves value to agents → they bring listings | Matterport, Zillow | 4 | 3 | 5
8 | Saved searches + alerts (email/WhatsApp) | Brings buyers back; WhatsApp is the main channel in RO | Zillow, Storia | 4 | 2 | 6
9 | Price history + 'days on market' | Transparency; negotiation help | Zillow | 3 | 2 | 4
10 | Virtual staging (empty rooms furnished, clearly labeled) | Empty flats sell worse; must be labeled to stay honest | Zillow, Matterport | 3 | 4 | 2
11 | Book a viewing slot from the tour | Turns a tour into a meeting directly | Zillow messaging | 4 | 2 | 6
12 | Annotations / notes in the tour (e.g. 'new boiler 2024') | Agents highlight value; builds trust | Matterport Mattertags | 3 | 2 | 4
13 | Compare 2 homes side by side (tours + facts) | Helps decide; keeps users on site | Original | 3 | 3 | 3
14 | Aerial / building exterior view | Block/building condition matters a lot in RO | Zillow SkyTour | 2 | 4 | 0
15 | Agency white-label tours (own logo) | Paid feature for agencies → revenue | Matterport | 3 | 2 | 4
Score = Impact × 2 − Effort (higher = do first). Edit the blue numbers; pick a Decision from the list.

## Questions for you
# | Question | Your answer
1 | Merge the admin branch into main after testing? (T06)
2 | Do you have an Anthropic API key for Maria? (T07)
3 | Phone only, or also a 360° camera? Which one? (T10)
4 | Where should the tour app run (VPS / Render / Fly)? Budget per month? (T08)
5 | Which suggestion first? (see Suggestions → Decision)
6 | Still want all repos private? (T03)